## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sambhunagar WS Scheme includin | SM/08633 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Sambhunagar Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Gosaba South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000590/2021-2022 | 2984/AD | 29/10/2021 | 29/10/2022 | M/S. S.S. ENTERPRISE | 160.98 | 142.97 | 88.82 | 81
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Sambhunagar WS Scheme includin | SM/08633 | Retrofitting | Hiring Motor launch for Canning Sub Division under Alipore Division, PHE Dte. in connection with execution & maintenance of different piped water supply schemes at different island in the district of South 24 parganas.(Period 01/01/2022 to 30/06/2022) | Assistant Engineer, Canning sub division |  | ORD/001462/2021-2022 | 1289/CSD | 17/12/2021 | 16/06/2022 | RAJKUMAR MANNA | 2.16 | 17.33 | 801.16 | 0
Total | [13 empty] | 163.14 | 160.3 | 98.26