## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Harbhangi Water Supply Scheme including one | SM/08636 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Harbhangi Water Supply Scheme (Habitation- Tetultala), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000085/2022-2023 | 277/CSD | 19/05/2022 | 28/06/2022 | PROJECT & MAINTENANCE | 4.77 | 0 | 0 | 85
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Harbhangi Water Supply Scheme including one | SM/08636 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Harbhangi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000207/2021-2022 | 1424/AD | 27/07/2021 | 27/07/2022 | PROJECT & MAINTENANCE | 129.74 | 0 | 0 | 97
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Harbhangi Water Supply Scheme including one | SM/08636 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Harbhangi Water Supply Scheme (Habitation- Narayantala, Naliakhali & Tetultala), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/000086/2022-2023 | 278/CSD | 19/05/2022 | 28/06/2022 | PROJECT & MAINTENANCE | 4.79 | 0 | 0 | 85
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Harbhangi Water Supply Scheme including one | SM/08636 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Harbhangi Water Supply Scheme (Habitation- Chharanekhali & Uttar Sonakhali), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division |  | ORD/000088/2022-2023 | 279/CSD | 19/05/2022 | 28/06/2022 | PROJECT & MAINTENANCE | 4.76 | 0 | 0 | 85
Total | [13 empty] | 144.06 | 0 | 0