## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Sumatinagar & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08792 | Retrofitting | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC =835] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000813/2022-2023 | 6754/AD | 15/11/2022 | 15/03/2023 | UCON | 140.93 | 19.13 | 13.57 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Sumatinagar & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08792 | Retrofitting | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000778/2022-2023 | 6649/AD | 14/11/2022 | 14/12/2022 | MONCON INDIA | 10.01 | 9.99 | 99.76 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Sumatinagar & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08792 | Retrofitting | Preparation of DPR including estimate for Providing FHTC at Manasadwip W/S Scheme (Phase-A) & Sumatinagar W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte.[ W/O NO 520/AD, 24.08.21, T.NO. 1791/AD, 21-22] |  |  | VCH/002609/2021-2022 | BP-2021-22-512 | 22/03/2022 | 22/03/2022 | INDRANIL DUTTA & ASSOCIATES | 2.35 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Sumatinagar & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08792 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000695/2023-2024 | 465/AD | 24/01/2024 | 24/01/2024 | Resource Division | 11.27 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Sumatinagar & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08792 | Retrofitting | Repairing of 1 no. Pump House, Earth Filling, Boundary Wall Painting and Repair, Approach Road at 2nd Tubewell site for Sumatinagar (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13569) (SM/09394) (SM/08792) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000347/2025-2026 | 3103/AD | 02/07/2025 | 16/08/2025 | M/S. MA BHABANI CONSTRUCTION | 5.58 | 0 | 0 | 0
Total | [13 empty] | 170.14 | 29.12 | 17.11