## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Haradhanpur Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08793 | Retrofitting | Preparation of DPR including estimate for Providing FHTC at Companirchar W/S Scheme (Phase-A), Haradhanpur W/S Scheme (Phase-A) & Krishnanagar W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [W/O No. 519/KSD, 24.8.21, T.No. 1784/AD, 21-22] |  |  | VCH/002604/2021-2022 | BP-2021-22-507 | 22/03/2022 | 22/03/2022 | LEMNISCATE | 3.53 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Haradhanpur Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08793 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000697/2023-2024 | 467/AD | 24/01/2024 | 24/01/2024 | Resource Division | 10.8 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Haradhanpur Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08793 | Retrofitting | Repairing of 1 no. Pump House, Earth Filling, Boundary Wall Painting and Repair, Approach Road at 1st Tubewell site for Haradhanpur (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14159) (SM/09393) (SM/08793) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000450/2025-2026 | 3568/AD | 25/07/2025 | 08/09/2025 | PALASH HALDAR | 8.12 | 0 | 0 | 0
Total | [13 empty] | 22.44 | 0 | 0