## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) | SM/08794 | Retrofitting | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kakdwip Akshaynagar (Zone-III) W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001042/2021-2022 | 2273/AD | 06/09/2021 | 13/09/2021 | M/S R.DUTTA & CO. | 2.76 | 2.76 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) | SM/08794 | Retrofitting | Route Survey for Providing FHTC at Kakdwip Akshaynagar (Zone-I) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001015/2021-2022 | 533/KSD | 01/09/2021 | 21/09/2021 | INDRANIL DUTTA & ASSOCIATES | 3.52 | 3.02 | 85.85 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) | SM/08794 | Retrofitting | Route Survey for Providing FHTC at Kakdwip Akshaynagar (Zone-III) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001017/2021-2022 | 535/KSD | 01/09/2021 | 21/09/2021 | ROY CHOWDHURY ASSOCIATES | 3.89 | 3.53 | 90.84 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) | SM/08794 | Retrofitting | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kakdwip Akshaynagar (Zone-II) W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001039/2021-2022 | 2270/AD | 06/09/2021 | 13/09/2021 | ROY CHOWDHURY ASSOCIATES | 3.48 | 3.48 | 100 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) | SM/08794 | Retrofitting | Preparation of DPR including estimate for Providing FHTC at Kakdwip Akshaynagar W/S Scheme (Phase-A), Gobindarampur W/S Scheme (Phase-A), Kashinagar W/S Scheme (Phase-A) & Srikrishnanagar W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001008/2021-2022 | 514/KSD | 24/08/2021 | 03/09/2021 | ROY CHOWDHURY ASSOCIATES | 4.7 | 4.7 | 100 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) | SM/08794 | Retrofitting | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kakdwip Akshaynagar (Zone-I) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001038/2021-2022 | 2269/AD | 06/09/2021 | 13/09/2021 | M/S R.DUTTA & CO. | 2.64 | 2.64 | 100 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) | SM/08794 | Retrofitting | Route Survey for Providing FHTC at Kakdwip Akshaynagar (Zone-II) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001016/2021-2022 | 534/KSD | 01/09/2021 | 21/09/2021 | M/S R.DUTTA & CO. | 3.89 | 3.38 | 86.83 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) | SM/08794 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000087/2022-2023 | 5590/AD | 29/09/2022 | 29/09/2022 | Resource Division | 14.31 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) | SM/08794 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000266/2023-2024 | 3065/AD | 28/09/2023 | 28/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) | SM/08794 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000379/2023-2024 | 3565/AD | 18/10/2023 | 18/10/2023 | Resource Division | 5.95 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) | SM/08794 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000596/2023-2024 | 95/AD | 03/01/2024 | 03/01/2024 | Resource Division | 27.86 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kakdwip Akshaynagar Water Supply Scheme, Block : Kakdwip, District- South 24 Pgs. (Phase-A) | SM/08794 | Retrofitting | Making and fixing of 40 nos. permanent display board of various retrofitting PWSS under JJM at Kakdwip and Namkhana Block (within Non-Riverine area) under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-A) (SM/09998) (SM/08794) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000836/2024-2025 | 4542/AD | 13/11/2024 | 13/12/2024 | ANANTA KUMAR GIRI | 6.29 | 0 | 0 | 100
Total | [13 empty] | 79.58 | 23.5 | 29.53