## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of ground water based Narayantala Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | SM/08798 | Retrofitting | Survey, Design and DPR preparation for Augmentation of ground water based Narayantala Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001844/2021-2022 | 687/CSD | 19/08/2021 | 03/09/2021 | HORIZEN | 4.12 | 4.05 | 98.25 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of ground water based Narayantala Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | SM/08798 | Retrofitting | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Retrofitting of Narayantala W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000816/2022-2023 | 6811/AD | 16/11/2022 | 26/04/2025 | HARIDAS DUTTA | 19.49 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of ground water based Narayantala Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | SM/08798 | Retrofitting | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 23.12.2022 to 30.06.2023 | Assistant Engineer, Diamond Harbour sub division |  | ORD/001753/2022-2023 | 460/HQ-II/AD | 22/12/2022 | 22/06/2023 | M/S P. B. CONSTRUCTION | 2.4 | 1.58 | 65.84 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of ground water based Narayantala Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | SM/08798 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000390/2023-2024 | 331/AD | 19/01/2024 | 19/01/2024 | Resource Division | 6.13 | 0 | 0 | 0
Total | [13 empty] | 32.14 | 5.63 | 17.51