## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Bishnupur & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08800 | Retrofitting | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Bishnupur (Zone - I and II) W/S scheme, Block : Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13117) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000383/2024-2025 | 3079/AD | 25/07/2024 | 24/08/2024 | RANJIT CONSTRUCTION | 11.67 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Bishnupur & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08800 | Retrofitting | Construction of 1 no. Pump House of size 5.40 mtr. x 3.60 mtr. at 4th Tubewell site for Bishnupur (Zone- I and II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13117) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000384/2024-2025 | 3080/AD | 25/07/2024 | 08/09/2024 | M/S AINUR ENTERPRISE | 7.18 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Bishnupur & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08800 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000693/2023-2024 | 463/AD | 24/01/2024 | 24/01/2024 | Resource Division | 16.99 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Bishnupur & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08800 | Retrofitting | Repairing of 1 no. Pump House, Land Development, Boundary Wall Painting and Repair and Approach Road at 2nd Tubewell site for Bishnupur (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13117) (SM/09358) (SM/08800) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000449/2025-2026 | 3567/AD | 25/07/2025 | 08/09/2025 | SWAPAN GUCHHAIT | 3.89 | 0 | 0 | 0
Total | [13 empty] | 39.72 | 0 | 0