## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kachuberia & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08801 | Retrofitting | Route Survey for Providing FHTC at Kachuberia W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001081/2021-2022 | 572/KSD | 10/09/2021 | 30/09/2021 | ROY CHOWDHURY ASSOCIATES | 4.6 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kachuberia & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08801 | Retrofitting | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kachuberia W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001055/2021-2022 | 2343/AD | 09/09/2021 | 16/09/2021 | ROY CHOWDHURY ASSOCIATES | 3.8 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kachuberia & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08801 | Retrofitting | Route Survey for Providing FHTC at Kachuberia W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001611/2021-2022 | 610KSD | 27/09/2021 | 04/10/2021 | ROY CHOWDHURY ASSOCIATES | 2.26 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kachuberia & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08801 | Retrofitting | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road at OHR Site for Augmentation of Kachuberia W/S Scheme, Block : Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000471/2024-2025 | 3457/AD | 23/08/2024 | 07/10/2024 | M/S SOURAV MAHAPATRA | 32.06 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Kachuberia & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08801 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000705/2023-2024 | 475/AD | 24/01/2024 | 24/01/2024 | Resource Division | 24.87 | 0 | 0 | 0
Total | [13 empty] | 67.59 | 0 | 0