## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Krishnanagar Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08803 | Retrofitting | Laying distribution system for additional works along the East side of Main Road for Augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part - Q) (SM/11747) (SM/09395) (SM/08803) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000551/2024-2025 | 3780/AD | 18/09/2024 | 18/10/2024 | KHOKAN MONDAL | 12.86 | 12.79 | 99.42 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Krishnanagar Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08803 | Retrofitting | Continuation order for the work of Laying distribution system along the East side of Main Road for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-N) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000422/2024-2025 | 3206/AD | 01/08/2024 | 31/08/2024 | KHOKAN MONDAL | 14.43 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Krishnanagar Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08803 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000698/2023-2024 | 468/AD | 24/01/2024 | 24/01/2024 | Resource Division | 10 | 0 | 0 | 0
Total | [13 empty] | 37.29 | 12.79 | 34.29