## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Gangasagar Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08804 | Retrofitting | Route Survey for Providing FHTC at Gangasagar Zone - I & Gangasagar Zone - II W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001028/2021-2022 | 542/KSD | 01/09/2021 | 21/09/2021 | INDRANIL DUTTA & ASSOCIATES | 4.57 | 4.57 | 99.85 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Gangasagar Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08804 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000324/2023-2024 | 3139/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.6 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Gangasagar Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08804 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000538/2023-2024 | 22/AD | 02/01/2024 | 02/01/2024 | Resource Division | 18.95 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Gangasagar Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08804 | Retrofitting | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main and FHTC for 1 year after completion of FHTC works for Augmentation of Gangasagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001166/2023-2024 | 3763/AD | 04/11/2023 | 28/06/2025 | PIKASU BOSE | 366.36 | 50.5 | 13.78 | 98
Total | [13 empty] | 390.49 | 55.06 | 14.1