## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Mandirtala & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08805 | Retrofitting | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Mandirtala W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001057/2021-2022 | 2345/AD | 09/09/2021 | 16/09/2021 | INDRANIL DUTTA & ASSOCIATES | 3.42 | 3.42 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Mandirtala & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08805 | Retrofitting | Route Survey for Providing FHTC at Mandirtala W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001083/2021-2022 | 574/KSD | 10/09/2021 | 30/09/2021 | INDRANIL DUTTA & ASSOCIATES | 4.6 | 4.59 | 99.85 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Mandirtala & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08805 | Retrofitting | Route Survey for Providing FHTC at Mandirtala W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001618/2021-2022 | 618/KSD | 27/09/2021 | 04/10/2021 | INDRANIL DUTTA & ASSOCIATES | 3.32 | 3.08 | 92.55 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Mandirtala & Its Adj Mouzas Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08805 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000706/2023-2024 | 476/AD | 24/01/2024 | 24/01/2024 | Resource Division | 21.22 | 0 | 0 | 0
Total | [13 empty] | 32.55 | 11.08 | 34.05