## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Naraharipur & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08810 | Retrofitting | Route Survey for Providing FHTC at Naraharipur W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001084/2021-2022 | 575/KSD | 01/09/2021 | 21/09/2021 | LEMNISCATE | 4.24 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Naraharipur & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08810 | Retrofitting | Route Survey for Providing FHTC at Naraharipur W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001608/2021-2022 | 606/KSD | 27/09/2021 | 04/10/2021 | LEMNISCATE | 1.55 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Naraharipur & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08810 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000327/2023-2024 | 3142/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Naraharipur & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08810 | Retrofitting | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Naraharipur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001171/2023-2024 | 3815/AD | 07/11/2023 | 02/09/2024 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 668.32 | 0 | 0 | 40
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Naraharipur & Its Adj Mouza Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08810 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000535/2023-2024 | 19/AD | 02/01/2024 | 02/01/2024 | Resource Division | 16.67 | 0 | 0 | 0
Total | [13 empty] | 691.08 | 0 | 0