## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 20 nos Mark-II hand pump tube wells to mitigate the acute water scarcity due to super cyclone YAAS. | SM/08986 | Disaster | Sinking of 09(Nine) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Gosaba Block (Chotomollakhali G.P.- 03 no, Kachukhali G.P.- 05 no, Rangabelia G.P- 01 no) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-B) | Assistant Engineer,HQ-I |  | ORD/001413/2021-2022 | 6156/AD | 21/02/2022 | 23/03/2022 | MD. NAZRUL ISLAM GAZI | 30.43 | 30.34 | 99.7 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 20 nos Mark-II hand pump tube wells to mitigate the acute water scarcity due to super cyclone YAAS. | SM/08986 | Disaster | Sinking of 05(Five) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 330 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Namkhana Block (Haripur G.P.- 02 no,Narayanpur G.P.- 03) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-D) | Assistant Engineer,HQ-I |  | ORD/001407/2021-2022 | 6152/AD | 21/02/2022 | 23/03/2022 | A.M. ENTERPRISE | 15.93 | 15.79 | 99.12 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 20 nos Mark-II hand pump tube wells to mitigate the acute water scarcity due to super cyclone YAAS. | SM/08986 | Disaster | Sinking of 05(Five) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 350 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Joynagar-I Block (Khakurdha G.P.-03 no, Jangaliya G.P.- 02 no,) due to affected by super Cyclon- "YAASH" in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. [PART-C] | Assistant Engineer,HQ-I |  | ORD/001527/2021-2022 | 6274/AD | 24/02/2022 | 26/03/2022 | M/S. L.P. CONSTRUCTION | 15.43 | 15.36 | 99.52 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 20 nos Mark-II hand pump tube wells to mitigate the acute water scarcity due to super cyclone YAAS. | SM/08986 | Disaster | Sinking of 05(Five) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Canning-I Block (Hatpukuria G.P.-02 no, Taldi G.P.-01 no, Nikarighata G.P.-01, Gopalpur G.P.-01 no.) due to affected by super Cyclon- YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-B) | Assistant Engineer,HQ-I |  | ORD/001388/2021-2022 | 6140/AD | 21/02/2022 | 23/03/2022 | SELIM GAZI | 13.65 | 3.25 | 23.81 | 0
Total | [13 empty] | 75.45 | 64.75 | 85.81