## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Resource | Engagement of implementation support agency (ISA) under JJM for implementation of awareness generation and capacity building activities at grassroots level in the district of South 24 Paraganas for 19 nos. blocks under Alipore Division PHE Dte. | SM/09003 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the South24 Parganas |  | Junior Engineer | ORD/000138/2022-2023 | 2858/RS | 20/05/2022 | 16/11/2022 | HALDAH EASTERN DEVELOPMENT SOCIETY | 186.44 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Resource | Engagement of implementation support agency (ISA) under JJM for implementation of awareness generation and capacity building activities at grassroots level in the district of South 24 Paraganas for 19 nos. blocks under Alipore Division PHE Dte. | SM/09003 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the South24 Parganas |  | Junior Engineer | ORD/000808/2022-2023 | 385/RS | 30/01/2023 | 29/07/2023 | HALDAH EASTERN DEVELOPMENT SOCIETY | 186.44 | 0 | 0 | 100
Total | [13 empty] | 372.89 | 0 | 0