## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Tilkumar Water Supply Scheme including one | SM/09007 | Retrofitting | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE EXECUTIVE ENGINEER, CDD, PHE DTE. |  |  | ORD/000061/2022-2023 | 77/ S&WSD | 27/05/2022 | 11/06/2022 | SUMAN KUMAR DEY | 0.9 | 0.37 | 41.31 | 0
2 | SOUTH 24 PARGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Tilkumar Water Supply Scheme including one | SM/09007 | Retrofitting | ADDITIONAL MOBILIZATION OF ALL MACHINERIES & ACCESSORIES ETC. AND SEALING OF SEALING ZONE AT SITE FOR CONSTRUCTION OF TUBE WELL AT TILKUMAR W/S SCH (UNTREATED ZONE), BASANTI BLOCK UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. |  |  | ORD/000218/2022-2023 | 257/CMSD-I | 23/06/2022 | 26/06/2022 | PADMA ENGINEERING & CO. | 0.92 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Tilkumar Water Supply Scheme including one | SM/09007 | Retrofitting | RESISTIVITY SURVEY OF TUBE WELLS AT IRPALA W/S SCHEME, UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000214/2021-2022 | 110/CMSD-I (D) | 20/07/2021 | 27/07/2021 | EARTH CARE PRODUCTS & SERVICES | 0.52 | 0.52 | 100 | 0
4 | SOUTH 24 PARGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Tilkumar Water Supply Scheme including one | SM/09007 | Retrofitting | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000251/2021-2022 | 214/CMSD-I(D) | 09/11/2021 | 24/11/2021 | PADMA ENGINEERING & CO. | 4.52 | 0.18 | 3.93 | 0
5 | SOUTH 24 PARGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Tilkumar Water Supply Scheme including one | SM/09007 | Retrofitting | PROVIDING DRILLING CREWS AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 350 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR TILKUMAR W/S SCHEME (UNTREATED ZONE), BASANTI BLOCK UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000015/2022-2023 | 52/CDD | 08/04/2022 | 08/05/2022 | PADMA ENGINEERING & CO. | 16.79 | 15.3 | 91.16 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Tilkumar Water Supply Scheme including one | SM/09007 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Tilkumar Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division |  | ORD/001151/2021-2022 | 5302/AD | 04/01/2022 | 04/01/2023 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 213.56 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Tilkumar Water Supply Scheme including one | SM/09007 | Retrofitting | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE ASSISTANT ENGINEER, STORE & WORKSHOP SUB DIVISION, CDD, PHE DTE. |  |  | ORD/000060/2022-2023 | 99/S&WSD | 23/06/2022 | 08/07/2022 | NAGENDRA PATRA | 0.87 | 0.75 | 86.2 | 33
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Tilkumar Water Supply Scheme including one | SM/09007 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000012/2021-2022 | 5618/AD | 25/01/2022 | 25/01/2022 | Resource Division | 22.69 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Tilkumar Water Supply Scheme including one | SM/09007 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000396/2023-2024 | 336/AD | 19/01/2024 | 19/01/2024 | Resource Division | 36.35 | 0 | 0 | 0
Total | [13 empty] | 297.12 | 17.12 | 5.76