## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 17 (seventeen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramchandrakhali Water Supply Scheme inclu | SM/09009 | Retrofitting | Inter connection and rising main for Tubewell No. 1, 2, 3 and 4 with supply of specials at Ramchandrakhali W/S Scheme (Zone-I), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000250/2023-2024 | 1393/AD | 12/07/2023 | 27/07/2023 | ARBINA ENTERPRISE | 16.29 | 14.31 | 87.84 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 17 (seventeen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramchandrakhali Water Supply Scheme inclu | SM/09009 | Retrofitting | Laying Distribution system for Ramchandrakhali W/S Scheme (Zone-I), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000665/2022-2023 | 6170/AD | 01/11/2022 | 18/02/2025 | M/S R.K.ENTERPRISE (SALBAGAN) | 227.75 | 141.24 | 62.02 | 100
Total | [13 empty] | 244.04 | 155.55 | 63.74