## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) includi | SM/09010 | Retrofitting | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-III & ABOVE) (NON AC) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH FOR THE OFFICE OF THE CALCUTTA MECHANICAL SUB DIVISION-I, PHE DTE. |  |  | ORD/000217/2021-2022 | 67/CMSD-I (D) | 22/03/2022 | 29/03/2022 | SUJATA BHOWMICK | 0.87 | 0.34 | 39.17 | 67
2 | SOUTH 24 PARGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) includi | SM/09010 | Retrofitting | ADDITIONAL TRANSPORTATION OF GRAVELS, SEALING AND OTHERS AT SITE FOR CONSTRUCTION OF TUBE WELL IN CHUNAKHALI W/S SCHEME (REPLACEMENT TW-III, Z-II), BASANTI BLOCK UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. |  |  | ORD/000222/2022-2023 | 309/CMSD-I | 08/07/2022 | 11/07/2022 | PADMA ENGINEERING & CO. | 0.92 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) includi | SM/09010 | Retrofitting | Relaying and repairing of pipe line for FHTC work at node point no. 124-122-121-120-33-34-36-89-88-87-85-38-40-50-51-52-55-56 of Chunakhali Water Supply Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000031/2022-2023 | 517/AD | 26/04/2022 | 26/05/2022 | R.S.CONSTRUCTION CO. | 45.81 | 45.75 | 99.86 | 100
4 | SOUTH 24 PARGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) includi | SM/09010 | Retrofitting | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000251/2021-2022 | 214/CMSD-I(D) | 09/11/2021 | 24/11/2021 | PADMA ENGINEERING & CO. | 4.52 | 1.05 | 23.24 | 0
5 | SOUTH 24 PARGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) includi | SM/09010 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 350 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR CHUNAKHALI W/S SCHEME (Z-II, REPLACEMENT TW-III), BASANTI BLOCK UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. |  |  | ORD/000024/2022-2023 | 51/CDD | 08/04/2022 | 08/05/2022 | PADMA ENGINEERING & CO. | 16.79 | 14.95 | 89.05 | 0
6 | SOUTH 24 PARGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) includi | SM/09010 | Retrofitting | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE ASSISTANT ENGINEER, STORE & WORKSHOP SUB DIVISION, CDD, PHE DTE. |  |  | ORD/000060/2022-2023 | 99/S&WSD | 23/06/2022 | 08/07/2022 | NAGENDRA PATRA | 0.87 | 0.78 | 88.77 | 33
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) includi | SM/09010 | Retrofitting | Relaying damaged pipeline for FHTC at Chunakhali W/S Scheme Chunakhali Primary School to H/O Shyamal Das and H/O Prasanta Das to Chowmatha at Buglakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001633/2020-2021 | 1349/CSD | 06/01/2021 | 05/02/2021 | SUKANTA HALDER | 4.73 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) includi | SM/09010 | Retrofitting | Relaying and repairing of damaged pipeline for FHTC at Chunakhali W/S Scheme at Khanka Sarif More to Sachiakhali FP School of Sachiakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001619/2020-2021 | 1345/CSD | 04/01/2021 | 03/02/2021 | MODERN CONSTRUCTION | 4.82 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) includi | SM/09010 | Retrofitting | Relaying damaged pipeline for FHTC at Chunakhali W/S Scheme at Laskarpara to PWD Road and H/O Ganesh Sardar to H/O Dinanath Sardar of Purba Bayar Sing Mouza and Sachiakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001632/2020-2021 | 1348/CSD | 06/01/2021 | 05/02/2021 | MODERN CONSTRUCTION | 4.68 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) includi | SM/09010 | Retrofitting | Repairing damaged pipeline for FHTC at Chunakhali W/S Scheme at Buglakhali Mouza, Purba Bayar Sing Mouza, Sachiakhali Mouza and Baria Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001637/2020-2021 | 1350/CSD | 06/01/2021 | 05/02/2021 | SUKANTA HALDER | 4.74 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) includi | SM/09010 | Retrofitting | Continuation order for the work of Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 of Augmentation of Chunakhali (Zone - I) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002438/2024-2025 | 623/AD | 17/02/2025 | 18/06/2025 | AQUATECH ENGINEER | 19.6 | 0 | 0 | 100
Total | [13 empty] | 108.35 | 62.87 | 58.02