## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Netra Water Supply Scheme including one year | SM/09014 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Netra Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division |  | ORD/000012/2021-2022 | 3020/AD | 02/11/2021 | 02/11/2022 | JAYANTA KUMAR DEY | 80.16 | 30.27 | 37.76 | 40
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Netra Water Supply Scheme including one year | SM/09014 | Retrofitting | 03 (three) nos. 40 mm dia. 375 mtr. deep Trial Bore by water jet method for Improvement & Retrofitting of Netra W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001383/2022-2023 | 1066/CSD | 15/12/2022 | 24/01/2023 | A.P. CONSTRUCTION | 0.96 | 0.32 | 33.33 | 95
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Netra Water Supply Scheme including one year | SM/09014 | Retrofitting | Additional laying of pipeline at Netra W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000068/2025-2026 | 2257/AD | 14/05/2025 | 28/06/2025 | SAHANA ENTERPRISE | 15.98 | 0 | 0 | 0
Total | [13 empty] | 97.1 | 30.59 | 31.5