## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Parbatipur Water Supply S | SM/09016 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Parbatipur Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000013/2021-2022 | 3021/AD | 02/11/2021 | 02/11/2022 | M/S A.K. GHATAK | 83.3 | 0 | 0 | 99
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Parbatipur Water Supply S | SM/09016 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Parbatipur Water Supply Scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ III) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000416/2023-2024 | 775/CSD | 02/08/2023 | 01/09/2023 | JOY MAA TARA ENTERPRISE | 4.57 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Parbatipur Water Supply S | SM/09016 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Parbatipur Water Supply Scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ II) | Assistant Engineer, Canning sub division |  | ORD/001466/2022-2023 | 1285/CSD | 31/01/2023 | 02/03/2023 | M.P. ENTERPRISE | 4.81 | 0 | 0 | 99
Total | [13 empty] | 92.68 | 0 | 0