## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taldi Water Supply Scheme including one year | SM/09017 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 5617/AD | 25/01/2022 | 25/01/2022 | Resource Division | 29.69 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taldi Water Supply Scheme including one year | SM/09017 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taldi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division |  | ORD/000849/2021-2022 | 4430/AD | 06/12/2021 | 06/12/2022 | SUPRITI ENTERPRISE | 277.8 | 0 | 0 | 32
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taldi Water Supply Scheme including one year | SM/09017 | Retrofitting | Laying of additional pipe line to cover the FHTC work and other allied works for Retrofitting of Taldi (Zone - I and II) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000602/2023-2024 | 2351/AD | 18/08/2023 | 02/10/2023 | SUPRITI ENTERPRISE | 53.79 | 0 | 0 | 100
Total | [13 empty] | 361.28 | 0 | 0