## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (Six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including o | SM/09075 | Retrofitting | Laying distribution system and allied works for Haripur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000127/2022-2023 | 2030/AD | 21/06/2022 | 21/07/2022 | M/S BOSE & CO. | 16.85 | 9.81 | 58.21 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (Six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including o | SM/09075 | Retrofitting | Laying distribution system and allied works for Haripur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000126/2022-2023 | 2029/AD | 21/06/2022 | 21/07/2022 | M/S BOSE & CO. | 18.21 | 17.13 | 94.03 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (Six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including o | SM/09075 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 5145/AD | 21/09/2022 | 21/09/2022 | Resource Division | 24.6 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (Six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including o | SM/09075 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000290/2023-2024 | 3085/AD | 28/09/2023 | 28/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (Six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including o | SM/09075 | Retrofitting | Operation and maintenance of distribution system including rising main and FHTC for Haripur Piped Water Supply Scheme of Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. (for 365 days) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000516/2024-2025 | 3614/AD | 06/09/2024 | 06/09/2025 | ASHIS ENTERPRISE | 6.19 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (Six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including o | SM/09075 | Retrofitting | Repairing of Pump House and Boundary wall, approach road at 4 nos Pump House site of Haripur (Zone-I) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18698) (SM/09075) (SM/09076) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000378/2025-2026 | 3253/AD | 09/07/2025 | 23/08/2025 | SAMANTA AND COMPANY | 4.35 | 0 | 0 | 0
Total | [13 empty] | 70.5 | 26.93 | 38.2