## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 05 (Five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including | SM/09076 | Retrofitting | Retrofitting of Distribution System including Providing Functional Household Tap Connection (FHTC) to the households of Haripur Water Supply Scheme, Block ¿ Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001568/2021-2022 | 6830/AD | 23/03/2022 | 07/05/2022 | BOSE & CO. | 115.98 | 17.26 | 14.88 | 80
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 05 (Five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haripur W/S Scheme including | SM/09076 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000795/2023-2024 | 640/AD | 30/01/2024 |  | Resource Division | 7.2 | 0 | 0 | 0
Total | [13 empty] | 123.18 | 17.26 | 14.01