## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Companirchar W/S Scheme includ | SM/09077 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of habitation ¿ Companir Char and Uttar Para at Companir Char Water Supply scheme, Block - Sagar, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001140/2021-2022 | 5530/AD | 20/01/2022 | 20/01/2023 | SWAPAN KUMAR PRADHAN | 36.94 | 34.14 | 92.44 | 94
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Companirchar W/S Scheme includ | SM/09077 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of habitation - Das Para and Majher Para at Companirchar Water Supply scheme, Block - Sagar, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001137/2021-2022 | 5529/AD | 20/01/2022 | 20/01/2023 | SANKAR HALDER | 28.77 | 27.46 | 95.45 | 96
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Companirchar W/S Scheme includ | SM/09077 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000025/2021-2022 | 5762/AD | 02/02/2022 |  | Resource Division | 206.4 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Companirchar W/S Scheme includ | SM/09077 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 1171/AD | 27/05/2022 |  | Resource Division | 3.98 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 06 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Companirchar W/S Scheme includ | SM/09077 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000700/2023-2024 | 470/AD | 24/01/2024 |  | Resource Division | 9.29 | 0 | 0 | 0
Total | [13 empty] | 285.37 | 61.6 | 21.59