## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Iswaripur Water Supply Scheme including one y | SM/09094 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Iswaripur Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division |  | ORD/001190/2021-2022 | 5708/AD | 31/01/2022 | 31/01/2023 | ASHIT BARAN BOSE | 84.89 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Iswaripur Water Supply Scheme including one y | SM/09094 | Retrofitting | Day to day annual operation, repair & maintenance of CI/DI/AC/UPVC Rising Main & Distribution System for different zones at Iswaripur W/S Scheme for 365 Days during financial year 2020-2021 and 2021-2022 under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000529/2020-2021 | 586/CSD | 27/08/2020 | 27/08/2021 | SUKANTA HALDER | 2.26 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Iswaripur Water Supply Scheme including one y | SM/09094 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 1175/AD | 27/05/2022 | 27/05/2022 | Resource Division | 3.98 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Iswaripur Water Supply Scheme including one y | SM/09094 | Retrofitting | Laying pipeline for dispose of waste water from IEP at Head Work Site of Iswaripur W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001973/2022-2023 | 12592/AD | 13/03/2023 | 28/03/2023 | BHUNIA BUILDERS | 5.97 | 0 | 0 | 100
Total | [13 empty] | 97.1 | 0 | 0