## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 16 (sixteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Athara Beki Water Supply Scheme including o | SM/09095 | Retrofitting | Day to day annual operation, repair & maintenance of CI/DI/AC/UPVC Rising Main & Distribution System for different zones at Atharabanki W/S Scheme for 365 Days during financial year 2020-2021 and 2021-2022 under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001765/2021-2022 | 710/CSD | 24/08/2021 | 24/08/2022 | MAA LAXMI ENTERPRISE | 4.78 | 3.19 | 66.82 | 73
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 16 (sixteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Athara Beki Water Supply Scheme including o | SM/09095 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000085/2022-2023 | 5548/AD | 29/09/2022 | 29/09/2022 | Resource Division | 9.24 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 16 (sixteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Athara Beki Water Supply Scheme including o | SM/09095 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 16 (sixteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Athara Beki Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001591/2021-2022 | 6962/AD | 29/03/2022 | 27/07/2022 | SAMSUL ENTERPRISE | 253.28 | 234.47 | 92.57 | 94
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 16 (sixteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Athara Beki Water Supply Scheme including o | SM/09095 | Retrofitting | Laying of Pipeline to connect the uncovered habitations of Atharabenki W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001577/2022-2023 | 11348/AD | 11/02/2023 | 12/05/2023 | SAMSUL ENTERPRISE | 130.98 | 6.81 | 5.2 | 95
Total | [13 empty] | 398.28 | 244.47 | 61.38