## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea | SM/09358 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households at Bishnupur Water Supply scheme, Block - Sagar, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000002/2022-2023 | 28/AD | 04/04/2022 | 19/05/2022 | M. MUKHERJEE | 114.37 | 111.56 | 97.54 | 98
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea | SM/09358 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000382/2023-2024 | 3568/AD | 18/10/2023 | 18/10/2023 | Resource Division | 10.38 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea | SM/09358 | Retrofitting | Hiring of Motor Launch for Kakdwip Sub Division under Alipore Division, P.H.E. Dte. in connection with execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas (Period from 01.12.2021 to 30.11.2022) |  |  | BILL/01170/2022-2023 | BP-2023-24-31 | 28/04/2023 | 28/04/2023 | RAJKUMAR MANNA | 6.06 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea | SM/09358 | Retrofitting | Hiring of Motor Launch for Kakdwip Sub Division under Alipore Division, P.H.E. Dte. in connection with execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas (Period from 01.12.2021 to 30.11.2022) |  |  | BILL/01169/2022-2023 | BP-2023-24-18 | 18/04/2023 | 18/04/2023 | RAJKUMAR MANNA | 6.51 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea | SM/09358 | Retrofitting | Surging of 3 nos. Tubewell for Augmentation of Bishnupur- 1 no., Mahishamari- 1 no., Kamalpur Rudranagar- 1 no. W/S Scheme under JJM, Block - Sagar under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000506/2024-2025 | 3607/AD | 06/09/2024 | 06/10/2024 | COPE ENTERPRISE | 5.34 | 1.78 | 33.33 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea | SM/09358 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000694/2023-2024 | 464/AD | 24/01/2024 | 24/01/2024 | Resource Division | 10.19 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea | SM/09358 | Retrofitting | Hiring of Motor Launch for Kakdwip Sub Division of Alipore Division, PHE Dte. (01.06.2022 to 31.08.2022) |  |  | BILL/03520/2023-2024 | BP-2023-24-1074 | 24/02/2024 | 24/02/2024 | RAJKUMAR MANNA | 6.51 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea | SM/09358 | Retrofitting | Repairing of 1 no. Pump House, Land Development, Boundary Wall Repair and Painting and Approach Road at 1st Tubewell site for Bishnupur (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13117) (SM/09358) (SM/08800) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000338/2025-2026 | 3044/AD | 30/06/2025 | 14/08/2025 | PALASH HALDAR | 5.71 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea | SM/09358 | Retrofitting | Repairing of 1 no. Pump House, Land Development, Boundary Wall Painting and Repair and Approach Road at 2nd Tubewell site for Bishnupur (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13117) (SM/09358) (SM/08800) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000449/2025-2026 | 3567/AD | 25/07/2025 | 08/09/2025 | SWAPAN GUCHHAIT | 3.89 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea | SM/09358 | Retrofitting | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Bishnupur W/S Scheme, Block - Sagar under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13117) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000448/2024-2025 | 3357/AD | 14/08/2024 | 01/01/2025 | SARADA CONSTRUCTION | 52.08 | 0 | 0 | 50
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea | SM/09358 | Retrofitting | Providing support services for data mapping of available data within command area for preparation of GMIS at Bishnupur (SM/13117) W/S Scheme, Block - Sagar of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000018/2025-2026 | 2004/AD | 28/04/2025 | 28/05/2025 | INDRANIL DUTTA & ASSOCIATES | 7.81 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea | SM/09358 | Retrofitting | Continuation order for the work of Construction of 2 nos. 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 2 nos. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Bishnupur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/003146/2023-2024 | 1752/AD | 27/03/2024 | 26/04/2024 | M/S. S.S. ENTERPRISE | 36.6 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (Ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bishnupur Water Supply Scheme including one yea | SM/09358 | Retrofitting | Hiring of Motor Launch for Kakdwip Sub Division of Alipore Division, PHE Dte. (01.06.2022 to 31.08.2022) |  |  | BILL/01907/2023-2024 |  | 17/10/2023 | 17/10/2023 | RAJKUMAR MANNA | 6.51 | 0 | 0 | 0
Total | [13 empty] | 271.98 | 113.34 | 41.67