## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 01 (One) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nebutala Water Supply Scheme including one year | SM/09359 | Retrofitting | Supply and delivery of 6/10 mm NB Gun-metal Ferrule for Providing Functional Household Tap Connection (FHTC) to the households of Nebutala W/S Scheme under JJM Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001751/2021-2022 | 238/KSD/Camp/G.S.Mela 22 | 31/01/2022 | 07/02/2022 | SHEKHAR CHAKRABORTY | 4.09 | 4.05 | 99.01 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 01 (One) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nebutala Water Supply Scheme including one year | SM/09359 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the all habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nebutala Water Supply Scheme, Block ¿ Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000572/2021-2022 | 3673/AD | 22/11/2021 | 22/11/2022 | SHEKHAR CHAKRABORTY | 53.74 | 41.76 | 77.71 | 70
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 01 (One) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nebutala Water Supply Scheme including one year | SM/09359 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 1168/AD | 27/05/2022 | 27/05/2022 | Resource Division | 5.97 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 01 (One) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nebutala Water Supply Scheme including one year | SM/09359 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000823/2023-2024 | 668/AD | 30/01/2024 | 30/01/2024 | Resource Division | 3.01 | 0 | 0 | 0
Total | [13 empty] | 66.8 | 45.81 | 68.57