## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 07 (Seven) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haradhanpur Water Supply Scheme including one | SM/09393 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households at Haradhanpur Water Supply scheme, Block - Sagar, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001142/2021-2022 | 5531/AD | 20/01/2022 | 20/01/2023 | UNIVERSAL CORPORATION | 68.89 | 66.5 | 96.54 | 97
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 07 (Seven) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haradhanpur Water Supply Scheme including one | SM/09393 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000016/2021-2022 | 5622/AD | 25/01/2022 | 25/01/2022 | Resource Division | 6.19 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 07 (Seven) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haradhanpur Water Supply Scheme including one | SM/09393 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 1169/AD | 27/05/2022 | 27/05/2022 | Resource Division | 3.98 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 07 (Seven) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haradhanpur Water Supply Scheme including one | SM/09393 | Retrofitting | Hiring of Diesel Car / Luxury Taxi for supervision of works of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.02.2023 to 31.07.2023. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002177/2022-2023 | 653/KSD | 31/01/2023 | 31/07/2023 | BADSHA ALOM | 2.39 | 1.76 | 73.79 | 70
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 07 (Seven) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Haradhanpur Water Supply Scheme including one | SM/09393 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000682/2023-2024 | 452/AD | 24/01/2024 | 24/01/2024 | Resource Division | 3.06 | 0 | 0 | 0
Total | [13 empty] | 84.51 | 68.27 | 80.78