## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 05 (Five) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Krishnanagar Water Supply Scheme including one | SM/09395 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000074/2022-2023 | 4849/AD | 21/09/2022 | 21/09/2022 | Resource Division | 24.6 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 05 (Five) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Krishnanagar Water Supply Scheme including one | SM/09395 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000378/2023-2024 | 3517/AD | 16/10/2023 | 16/10/2023 | Resource Division | 14.31 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 05 (Five) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Krishnanagar Water Supply Scheme including one | SM/09395 | Retrofitting | Continuation work order for the work of Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 01.03.2024 to 30.06.2024. | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/003075/2023-2024 | 1142/AD | 27/02/2024 | 27/06/2024 | M/S P. B. CONSTRUCTION | 1.6 | 1.58 | 98.99 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 05 (Five) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Krishnanagar Water Supply Scheme including one | SM/09395 | Retrofitting | Laying distribution system for additional works along the East side of Main Road for Augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part - S) (SM/11747) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000759/2024-2025 | 4442/AD | 06/11/2024 | 06/12/2024 | M/S. MANDAL ENTERPRISE | 9.79 | 9.78 | 99.99 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 05 (Five) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Krishnanagar Water Supply Scheme including one | SM/09395 | Retrofitting | HIRING OF AN INSPECTION VEHICLE (DIESEL OPERATED WITH LUXURY PERMIT) FOR USE OF ASSISTANT ENGINEER (HQ-II), ALIPORE DIVISION, PHE DTE. (FOR THE PERIOD FROM 01.09.2024 TO 28.02.2025) | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000864/2024-2025 | 3534/HQ-II/AD | 30/08/2024 | 28/02/2025 | BINDU PRASAD DEVI | 2.4 | 2.22 | 92.69 | 55
Total | [13 empty] | 52.7 | 13.59 | 25.8