## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-III, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09397 | Retrofitting | Extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Dakatmari area under Krishnachandrapur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001589/2021-2022 | 773/RSD | 28/03/2022 | 27/05/2022 | M/S M. ENTERPRISE | 4.79 | 4.79 | 100 | 98
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-III, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09397 | Retrofitting | Supply and delivery at site of different dia. Specials in connection with laying distribution system of piped water supply at Zone - III (Krishnachandrapur PWSS) Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000611/2023-2024 | 242/RSD | 22/08/2023 | 21/09/2023 | M/S. M.M. ENTERPRISE | 4.49 | 4.49 | 100 | 98
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-III, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09397 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000034/2021-2022 | 6489/AD | 08/03/2022 | 08/03/2022 | Resource Division | 32.96 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-III, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09397 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 1680/AD | 13/06/2022 | 13/06/2022 | Resource Division | 15.38 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-III, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09397 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 3586/AD | 29/07/2022 | 29/07/2022 | Resource Division | 56.23 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-III, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09397 | Retrofitting | Remodeling of Distribution System of Krishnachandrapur PWS Scheme as Zone-III of Mathurapur - I Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000034/2022-2023 | 597/AD | 28/04/2022 | 28/05/2022 | M/S B.M. CONSTRUCTION | 95.84 | 25.66 | 26.78 | 50
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-III, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09397 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-I, Zone-III (Krishnachandrapur PWSS) including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001453/2021-2022 | 6069/AD | 17/02/2022 | 17/02/2023 | M/S B.M. CONSTRUCTION | 128.45 | 66.71 | 51.94 | 99
Total | [13 empty] | 338.14 | 101.66 | 30.06