## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/09398 | Retrofitting | Miscellaneous work for smooth distribution system of piped water supply at Zone-VI of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000439/2022-2023 | 4353/AD | 25/08/2022 | 24/10/2022 | DEBARATI ENTERPRISE | 49.88 | 33.17 | 66.51 | 99
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/09398 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000019/2021-2022 | 5625/AD | 25/01/2022 | 25/01/2022 | Resource Division | 9.31 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/09398 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 1170/AD | 27/05/2022 | 27/05/2022 | Resource Division | 5.97 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/09398 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 1678/AD | 13/06/2022 | 13/06/2022 | Resource Division | 15.4 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/09398 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 3585/AD | 29/07/2022 | 29/07/2022 | Resource Division | 48.96 | 0 | 0 | 0
Total | [13 empty] | 129.52 | 33.17 | 25.61