## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-V, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/09399 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-II, Zone-V (Raidighi PWSS) including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001340/2021-2022 | 6034/AD | 16/02/2022 | 16/02/2023 | TANMAY ROY CHOWDHURY | 171.21 | 0 | 0 | 85
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-V, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/09399 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 1681/AD | 13/06/2022 | 13/06/2022 | Resource Division | 15.4 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-V, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/09399 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000096/2022-2023 | 6202/AD | 02/11/2022 | 02/11/2022 | Resource Division | 76.28 | 0 | 0 | 0
Total | [13 empty] | 262.88 | 0 | 0