## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-II, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09400 | Retrofitting | Repairing of pump house 1 and approach road and plinth protection including boundary wall at Khari (Zone-I) W/S Scheme, modified as Zone- II of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000997/2023-2024 | 294/RSD | 29/09/2023 | 28/11/2023 | TIYASHA ENTERPRISE | 2.99 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-II, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09400 | Retrofitting | Repairing of pump house 2 and approach road and plinth protection at Khari (Zone-II) W/S Scheme, modified as Zone- II of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001004/2023-2024 | 297/RSD | 29/09/2023 | 28/11/2023 | SUKUMAR HALDAR | 2.26 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-II, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09400 | Retrofitting | Repairing of pump house ¿ 2 and approach road and plinth protection including boundary wall at Khari (Zone-I) W/S Scheme, modified as Zone- II of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001001/2023-2024 | 295/RSD | 29/09/2023 | 28/11/2023 | JOY MAA TARA ENTERPRISE | 3.14 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-II, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09400 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 5148/AD | 21/09/2022 | 21/09/2022 | Resource Division | 24.6 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-II, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09400 | Retrofitting | Providing FHTC including distribution system and other allied works at Zone- II, Mathurapur-II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle. | ORD/000345/2023-2024 | 3372/AD | 11/10/2023 | 02/07/2025 | M/S. TAPAS MONDAL | 114.8 | 0 | 0 | 20
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-II, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09400 | Retrofitting | Repairing of pump house 3 and approach road and plinth protection including boundary wall at Khari (Zone-II) W/S Scheme, modified as Zone- II of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001002/2023-2024 | 296/RSD | 29/09/2023 | 28/11/2023 | SUKUMAR HALDAR | 3.11 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-II, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09400 | Retrofitting | Inter connection between tubewells and Rising Main system of piped water supply at Zone - I of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001912/2023-2024 | 1434/AD | 09/03/2024 | 08/04/2024 | NITYANANDA MONDAL | 14.82 | 0 | 0 | 95
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-II, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09400 | Retrofitting | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-I, II, III, IV, V), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle. | ORD/000043/2025-2026 | 2071/AD | 30/04/2025 | 29/06/2025 | M/S B. ENTERPRISE | 27.24 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-II, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09400 | Retrofitting | Laying distribution system of piped water supply at Zone- I of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division,Junior Engineer1, Raidghi Sub Division | ORD/002254/2024-2025 | 556/AD | 12/02/2025 | 12/06/2025 | M/S BANERJEE ENGINEERING SYSTEM | 27.31 | 0 | 0 | 0
Total | [13 empty] | 220.26 | 0 | 0