## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IV, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09401 | Retrofitting | Laying distribution system of piped water supply at Zone-IV of Mathurapur - II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle.,Junior Engineer1, Raidghi Sub Division | ORD/000016/2022-2023 | 212/AD | 11/04/2022 | 08/09/2025 | UNITED BUILDERS | 337.79 | 102.13 | 30.23 | 70
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IV, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09401 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-II, Zone-IV (Gilarchat PWSS) including Operation & Maintenance of scheme for 1 (one) year under "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur", District-South 24-Parganas, Block-Mathurapur-II under Raidighi Sub-Division of Alipore Division, PHE Dte. (Phase-I). | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle.,Junior Engineer1, Raidghi Sub Division | ORD/000013/2022-2023 | 205/AD | 11/04/2022 | 01/02/2025 | MAHAVIR PUMPS MANUFACTURING PVT. LTD | 251.07 | 112.65 | 44.87 | 50
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IV, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09401 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000659/2023-2024 | 263/AD | 15/01/2024 | 15/01/2024 | Resource Division | 33.26 | 0 | 0 | 0
Total | [13 empty] | 622.12 | 214.78 | 34.52