## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VIII, Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Jeevan under Mega Surface Water Based Water Supply Scheme for Fa | SM/09425 | Retrofitting | Construction of platform of size 600mm x 600mm (inner dimension) for the existing FHTC along with road restoration at Gazipur, Tajpur, Sasan, Pikhira, Purba Gopalpur and Fatepur Village of Zone-VIII under Falta Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000584/2022-2023 | 5860/AD | 18/10/2022 | 02/12/2022 | SUPRITI ENTERPRISE | 64.93 | 35.37 | 54.47 | 55
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VIII, Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Jeevan under Mega Surface Water Based Water Supply Scheme for Fa | SM/09425 | Retrofitting | Construction of platform of size 600mm x 600mm (inner dimension) for the existing FHTC along with road restoration at Rantan, Chaluary, Niogirhat, Durbarat, Kotaldanga, Benapukur, Shibpur, Ramrampur, Mayna and Kalaria Village of Zone-VIII under Falta Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000585/2022-2023 | 5861/AD | 18/10/2022 | 02/12/2022 | SUPRITI ENTERPRISE | 63.77 | 21.25 | 33.32 | 45
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VIII, Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Jeevan under Mega Surface Water Based Water Supply Scheme for Fa | SM/09425 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000122/2022-2023 | 12048/AD | 27/02/2023 | 27/02/2023 | Resource Division | 2.61 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VIII, Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Jeevan under Mega Surface Water Based Water Supply Scheme for Fa | SM/09425 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000437/2023-2024 | 3619/AD | 30/10/2023 | 30/10/2023 | Resource Division | 33.88 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VIII, Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Jeevan under Mega Surface Water Based Water Supply Scheme for Fa | SM/09425 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000435/2023-2024 | 3627/AD | 30/10/2023 | 30/10/2023 | Resource Division | 6.16 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VIII, Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Jeevan under Mega Surface Water Based Water Supply Scheme for Fa | SM/09425 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VIII including Operation & Maintenance of scheme for 1 (one) year under "Mega Surface Water based Water Supply Scheme for Falta-Mathurapur" District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000009/2022-2023 | 139/AD | 07/04/2022 | 22/03/2025 | TANMAY ROY CHOWDHURY | 277.27 | 179.32 | 64.67 | 90
Total | [13 empty] | 448.62 | 235.93 | 52.59