## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SRIKRISHNANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09435 | Augmentation | Laying distribution system along with rising main for Augmentation of Srikrishnanagar Water Supply Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001483/2021-2022 | 6393/AD | 02/03/2022 | 01/05/2022 | SARADA CONSTRUCTION | 71.83 | 69.74 | 97.1 | 98
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SRIKRISHNANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09435 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SRIKRISHNANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000498/2022-2023 | 314/AD | 13/04/2022 | 28/05/2022 | LEMNISCATE | 1.79 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SRIKRISHNANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09435 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000056/2022-2023 | 3915/AD | 12/08/2022 | 12/08/2022 | Resource Division | 9.19 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SRIKRISHNANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09435 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000267/2023-2024 | 3065/AD | 28/09/2023 | 28/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SRIKRISHNANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09435 | Augmentation | Providing Functional Household Tap Connection (FHTC) to all the households in Srikrishnanagar Water Supply Scheme, Block - Kakdwip South 24 Pgs. District under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division | ORD/000400/2020-2021 | 3855/AD | 03/12/2020 | 03/12/2021 | L.N. ENTERPRISE | 27.43 | 23.5 | 85.67 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SRIKRISHNANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09435 | Augmentation | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Srikrishnanagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/09435) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000206/2024-2025 | 2589/AD | 19/06/2024 | 03/08/2024 | SARADA CONSTRUCTION | 34.89 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SRIKRISHNANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09435 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000673/2023-2024 | 439/AD | 24/01/2024 | 24/01/2024 | Resource Division | 2.22 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SRIKRISHNANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09435 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000828/2023-2024 | 673/AD | 30/01/2024 | 30/01/2024 | Resource Division | 4.19 | 0 | 0 | 0
Total | [13 empty] | 151.83 | 93.24 | 61.41