## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC of Ground Water Based Gangadharpur Water Supply Scheme (Phase - A) | SM/09467 | Retrofitting | Retrofitting of Distribution System including Providing Functional Household Tap Connection (FHTC) to the households of Gangadharpur Water Supply Scheme , Block ¿ Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E.Dte.(Phase-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001145/2021-2022 | 5533/AD | 20/01/2022 | 20/01/2023 | JAI BHARAT COMMERCIAL CORPORATION | 51.59 | 29.85 | 57.86 | 58
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC of Ground Water Based Gangadharpur Water Supply Scheme (Phase - A) | SM/09467 | Retrofitting | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Gangadharpur (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000323/2022-2023 | 3870/AD | 08/08/2022 | 07/09/2022 | M/S PIR BABA ENTERPRISE | 5.96 | 5.72 | 95.95 | 50
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC of Ground Water Based Gangadharpur Water Supply Scheme (Phase - A) | SM/09467 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000018/2021-2022 | 5624/AD | 25/01/2022 | 25/01/2022 | Resource Division | 4.4 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC of Ground Water Based Gangadharpur Water Supply Scheme (Phase - A) | SM/09467 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000273/2023-2024 | 3072/AD | 28/09/2023 | 28/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting for Providing FHTC of Ground Water Based Gangadharpur Water Supply Scheme (Phase - A) | SM/09467 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000803/2023-2024 | 648/AD | 30/01/2024 | 30/01/2024 | Resource Division | 3.79 | 0 | 0 | 0
Total | [13 empty] | 66.05 | 35.57 | 53.86