## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC of Ground Water Based Gobindarampur Water Supply Scheme (Phase - A) | SM/09468 | Retrofitting | Route Survey for Providing FHTC at Gobindarampur W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001025/2021-2022 | 539/KSD | 01/09/2021 | 21/09/2021 | ROY CHOWDHURY ASSOCIATES | 4.58 | 4.58 | 99.85 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC of Ground Water Based Gobindarampur Water Supply Scheme (Phase - A) | SM/09468 | Retrofitting | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Gobindarampur W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001044/2021-2022 | 2275/AD | 06/09/2021 | 13/09/2021 | INDRANIL DUTTA & ASSOCIATES | 3.04 | 3.04 | 100 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC of Ground Water Based Gobindarampur Water Supply Scheme (Phase - A) | SM/09468 | Retrofitting | Route Survey for Providing FHTC at Gobindarampur W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001609/2021-2022 | 607/KSD | 27/09/2021 | 04/10/2021 | ROY CHOWDHURY ASSOCIATES | 4.02 | 2.95 | 73.33 | 100
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC of Ground Water Based Gobindarampur Water Supply Scheme (Phase - A) | SM/09468 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000268/2023-2024 | 3067/AD | 28/09/2023 |  | Resource Division | 0.3 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC of Ground Water Based Gobindarampur Water Supply Scheme (Phase - A) | SM/09468 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000830/2023-2024 | 675/AD | 30/01/2024 |  | Resource Division | 18.1 | 0 | 0 | 0
Total | [13 empty] | 30.05 | 10.57 | 35.16