## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | SM/09469 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mahis Gheri, for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001835/2020-2021 | 1266/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.24 | 3.33 | 78.56 | 80
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | SM/09469 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mollar Chak & Shivnagar for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001792/2020-2021 | 1237/KSD | 23/02/2021 | 05/03/2021 | M/S MODINA ENTERPRISE | 4.55 | 3.82 | 84.01 | 84
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | SM/09469 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Khorimutha for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001849/2020-2021 | 1280/KSD | 23/02/2021 | 05/03/2021 | M/S MODINA ENTERPRISE | 4.1 | 3.72 | 90.56 | 91
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | SM/09469 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001846/2020-2021 | 1277/KSD | 23/02/2021 | 05/03/2021 | KHOKAN MONDAL | 4.74 | 4.7 | 99.1 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | SM/09469 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001808/2020-2021 | 1246/KSD | 23/02/2021 | 05/03/2021 | KHOKAN MONDAL | 4.76 | 4.53 | 95.13 | 96
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | SM/09469 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Village :- Debnibus & Bijoybati of Debnibus W/S Scheme, Block -Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. Part-B | Assistant Engineer, Kakdwip Sub Division |  | ORD/001853/2020-2021 | 1284/KSD | 23/02/2021 | 05/03/2021 | SUMAN ENTERPRISE | 4.46 | 0.15 | 3.46 | 87
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | SM/09469 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Sitala Mandir Para, for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001863/2020-2021 | 1294/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.24 | 4.24 | 100 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | SM/09469 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Para (Part) & Gosta Para (Part), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001897/2020-2021 | 1319/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.24 | 4.24 | 100 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | SM/09469 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Library Para, for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001839/2020-2021 | 1270/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.24 | 4.24 | 100 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | SM/09469 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kamar Para (Part) & Library Para (Part), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001762/2020-2021 | 1221/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.25 | 4.25 | 100 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | SM/09469 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttar Para, for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001860/2020-2021 | 1291/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.24 | 4.24 | 100 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | SM/09469 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gosta Para (Phase-II), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001843/2020-2021 | 1274/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.25 | 4.24 | 99.91 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | SM/09469 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Hari Mandir Para (Phase-II), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001741/2020-2021 | 1214/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.24 | 4.24 | 100 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | SM/09469 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Jameson Island & Kali Mandir Para (Part), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001729/2020-2021 | 1211/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.25 | 4.25 | 100 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone | SM/09469 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000775/2023-2024 | 609/AD | 29/01/2024 | 29/01/2024 | Resource Division | 14.15 | 0 | 0 | 0
Total | [13 empty] | 74.96 | 54.2 | 72.31