## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VII, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply S | SM/09507 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 5619/AD | 25/01/2022 | 25/01/2022 | Resource Division | 17.45 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VII, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply S | SM/09507 | Retrofitting | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/05/2023 to 31/10/2023) | Assistant Engineer, Diamond Harbour sub division |  | ORD/000080/2023-2024 | 23/DHSD | 25/04/2023 | 26/10/2023 | GOPAL KUMAR JHA | 2.4 | 1.9 | 79.32 | 50
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VII, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply S | SM/09507 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000614/2023-2024 | 293/AD | 15/01/2024 | 15/01/2024 | Resource Division | 12.32 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VII, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply S | SM/09507 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Diamond Harbour-II, Zone-VII including Operation and Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001150/2021-2022 | 5301/AD | 04/01/2022 | 31/03/2026 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 137.23 | 0 | 0 | 25
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-VII, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply S | SM/09507 | Retrofitting | Augmentation of laying distribution system including construction of 600 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system with allied works in Zone-VII at Kamarpole of Diamond Harbour- II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-950] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000305/2023-2024 | 1508/AD | 15/07/2023 | 24/10/2026 | JYOTY SOLAR POWER | 423.33 | 15.19 | 3.59 | 15
Total | [13 empty] | 592.73 | 17.09 | 2.88