## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IV, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Sc | SM/09508 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Diamond Harbour-II, Zone-IV including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division |  | ORD/001325/2021-2022 | 5934/AD | 11/02/2022 | 11/02/2023 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 366.63 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IV, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Sc | SM/09508 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000120/2022-2023 | 12050/AD | 27/02/2023 | 27/02/2023 | Resource Division | 3.51 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IV, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Sc | SM/09508 | Retrofitting | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-II (Netra, OHR Size-900) within Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/002369/2022-2023 | 322/DHSD | 07/11/2022 | 14/11/2022 | ASTER CONSULTANCY | 0.5 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IV, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Sc | SM/09508 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000877/2023-2024 | 751/AD | 03/02/2024 | 03/02/2024 | Resource Division | 17.38 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IV, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Sc | SM/09508 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000922/2023-2024 | 1264/AD | 02/03/2024 | 02/03/2024 | Resource Division | 0.62 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IV, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Sc | SM/09508 | Retrofitting | Augmentation of laying distribution system to extend the benefit of 100% FHTC household by providing Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-IV of Diamond Harbour-II block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 1450] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000341/2023-2024 | 3601/AD | 25/10/2023 | 25/06/2025 | CREATION CONSTRUCTION | 403.02 | 0 | 0 | 37
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IV, Diamond Harbour-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Sc | SM/09508 | Retrofitting | Interconnection from secondary grid to OHR and laying in the left-out portion of distribution system of different dia. DI pipes i.e. 200mm, 300mm, 450mm along with 63mm to 280mm UPVC pipes with allied road restoration work under augmentation scheme of Zone-IV of Diamond Harbour-II Block under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [SM/09508, SM/13912, SM/13914] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002529/2024-2025 | 814/AD | 27/02/2025 | 22/02/2026 | K.P. CONSTRUCTION | 146.09 | 0 | 0 | 52
Total | [13 empty] | 937.75 | 0 | 0