## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jibantala Water Supply Scheme including one year | SM/09509 | Retrofitting | Submission of power supply connection for Jibantala W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | VCH/001719/2022-2023 | BP-2022-23-432 | 17/11/2022 | 17/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 5.53 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jibantala Water Supply Scheme including one year | SM/09509 | Retrofitting | Submission of power supply connection for Jibantala W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | VCH/001720/2022-2023 | BP-2022-23-431 | 17/11/2022 | 17/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 3.58 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jibantala Water Supply Scheme including one year | SM/09509 | Retrofitting | Inter connection from TW No. -1, 2 and 3 to distribution line and supply materials at Jibantala Water Supply Scheme (Zone-I), Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000073/2022-2023 | 1037/AD | 23/05/2022 | 22/06/2022 | KAMALA ENTERPRISE (I) | 7.68 | 6.77 | 88.11 | 95
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jibantala Water Supply Scheme including one year | SM/09509 | Retrofitting | Submission of power supply quotation for the PH No.1, zone II of Jibantala W/S Scheme under SMD |  |  | BILL/00006/2022-2023 | BP-2022-23-503 | 12/12/2022 | 12/12/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 6.59 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jibantala Water Supply Scheme including one year | SM/09509 | Retrofitting | Submission of power supply quotation for the P/H No. 1, zone-II of Jibantala W/S Scheme under SMD |  |  | BILL/00007/2022-2023 | BP-2022-23-504 | 12/12/2022 | 12/12/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 3.41 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jibantala Water Supply Scheme including one year | SM/09509 | Retrofitting | Submission of power supply quotation for the P/H No. 1, zone-II of Jibantala W/S Scheme under SMD |  |  | BILL/00040/2022-2023 | BP-2022-23-504 | 12/12/2022 | 12/12/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 0.38 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jibantala Water Supply Scheme including one year | SM/09509 | Retrofitting | Submission of power supply quotation for the PH No.1, zone II of Jibantala W/S Scheme under SMD |  |  | BILL/00039/2022-2023 | BP-2022-23-503 | 12/12/2022 | 12/12/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 0.38 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jibantala Water Supply Scheme including one year | SM/09509 | Retrofitting | Laying of additional pipe line to cover the FHTC work and other allied works for Jibantala (Zone - I) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002057/2023-2024 | 573/AD | 29/01/2024 | 27/07/2024 | ANKUSH CONSTRUCTION AND CO. | 26.61 | 1.18 | 4.44 | 70
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jibantala Water Supply Scheme including one year | SM/09509 | Retrofitting | Laying of additional pipeline with other allied works at Jibantala (Zone-I & II) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001030/2024-2025 | 4940/AD | 03/12/2024 | 17/01/2025 | M/S. JHARNA ENTERPRISE | 20.96 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jibantala Water Supply Scheme including one year | SM/09509 | Retrofitting | Laying of additional pipe line to cover the FHTC work and other allied works for Jibantala (Zone - II) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002056/2023-2024 | 572/AD | 29/01/2024 | 29/03/2025 | VISHAL CONSTRUCTION CO. | 93.43 | 34.16 | 36.56 | 90
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jibantala Water Supply Scheme including one year | SM/09509 | Retrofitting | Construction of boundary wall at Pump House - 2 for Jibantala (Zone - II) Water Supply Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002131/2024-2025 | 390/AD | 30/01/2025 | 01/03/2025 | KUNDU CONSTRUCTION CO. | 14.2 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Jibantala Water Supply Scheme including one year | SM/09509 | Retrofitting | Construction of boundary wall at Pump House - 2 for Jibantala (Zone - I) Water Supply Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000688/2024-2025 | 4293/AD | 29/10/2024 | 31/05/2025 | KUNDU CONSTRUCTION CO. | 14.2 | 0 | 0 | 100
Total | [13 empty] | 196.97 | 42.11 | 21.38