## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Sankarpur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & J | SM/09512 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Sankarpur piped water supply scheme ( Mathurapur-I, Zone-XIV) including Operation & Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division |  | ORD/000571/2021-2022 | 3672/AD | 22/11/2021 | 22/11/2022 | M/S B.M. CONSTRUCTION | 82 | 74.34 | 90.65 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Sankarpur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & J | SM/09512 | Retrofitting | Parallel extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Birampur mouza (Node No. 176-177-178-179-180-181-182-184-185) of Sankarpur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001586/2021-2022 | 770/RSD | 28/03/2022 | 27/05/2022 | M/S B.M. CONSTRUCTION | 4.78 | 4.78 | 100 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Sankarpur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & J | SM/09512 | Retrofitting | Extension of pipe line for providing FHTC at Zone-XIV of Mathurapur - I Block (Andharmanik & Sankarpur purba para) under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001767/2021-2022 | 625/RSD | 29/12/2021 | 13/01/2022 | M/S M. ENTERPRISE | 4.75 | 4.75 | 100 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Sankarpur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & J | SM/09512 | Retrofitting | Dismantling and road restoration in connection with Laying distrubution system of piped water supply at Zone - XIV (Mouza Birampur & Dakhin Janardanpur) of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (PART - A) | Assistant Engineer, Raidighi sub division |  | ORD/001793/2022-2023 | 927/RSD | 10/03/2023 | 09/04/2023 | M/S B.N.ENTERPRISE | 4.82 | 3.47 | 71.96 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Sankarpur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & J | SM/09512 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000021/2021-2022 | 5658/AD | 27/01/2022 | 27/01/2022 | Resource Division | 1.19 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Sankarpur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & J | SM/09512 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000643/2023-2024 | 247/AD | 15/01/2024 | 15/01/2024 | Resource Division | 12.06 | 0 | 0 | 0
Total | [13 empty] | 109.6 | 87.34 | 79.68