## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Purba Ranaghat piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM | SM/09513 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Purba Ranaghat piped water supply scheme ( Mathurapur-I, Zone-IV) including Operation and Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Raidighi sub division |  | ORD/000570/2021-2022 | 3671/AD | 22/11/2021 | 22/11/2022 | RANADHIR SINHA | 61.42 | 54.14 | 88.15 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Purba Ranaghat piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM | SM/09513 | Retrofitting | Laying distribution system of piped water supply at Zone-IV of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000480/2021-2022 | 2438/AD | 16/09/2021 | 15/11/2021 | M/S KALPANA CONSTRUCTION | 50.59 | 0.74 | 1.47 | 95
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Purba Ranaghat piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM | SM/09513 | Retrofitting | Estimate for parallel distribution line for providing FHTC at Purba Ranaghata W/S scheme of Mathurapur - I Block under ?Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas? under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001772/2021-2022 | 630/RSD | 29/12/2021 | 13/01/2022 | M/S G.M. ASSOCIATES | 4.79 | 4.79 | 100 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Purba Ranaghat piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM | SM/09513 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 5659/AD | 27/01/2022 | 27/01/2022 | Resource Division | 1 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Purba Ranaghat piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM | SM/09513 | Retrofitting | Parallel distribution pipeline to provide FHTC at Purba Ranaghata mouza under Zone-IV of Mathurapur-I block, under Surface water based water supply scheme Falta- Mathurapur of Raidighi Sub-Division under Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001134/2022-2023 | 599/RSD | 23/12/2022 | 22/01/2023 | SUPER CONSTRUCTION | 4.53 | 4.27 | 94.22 | 95
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Purba Ranaghat piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM | SM/09513 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000604/2023-2024 | 234/AD | 11/01/2024 | 11/01/2024 | Resource Division | 9.69 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Purba Ranaghat piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM | SM/09513 | Retrofitting | Laying distribution system of piped water supply at Zone- IV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division,Junior Engineer1, Raidghi Sub Division | ORD/000661/2024-2025 | 4207/AD | 23/10/2024 | 07/12/2024 | M/S. L.P. CONSTRUCTION | 18.75 | 2.32 | 12.35 | 100
Total | [13 empty] | 150.76 | 66.26 | 43.95