## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Extension of pipeline to provide Functional Household Tap Connection (FHTC) and construction of sluice valve chamber under Krishnarampur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000219/2022-2023 | 3060/AD | 13/07/2022 | 12/08/2022 | KAKALI ENTERPRISE | 8.06 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Krishnarampur piped water supply scheme ( Mathurapur-I, Zone-X) including Operation & Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) (2nd call) | Assistant Engineer, Raidighi sub division |  | ORD/001199/2021-2022 | 5725/AD | 31/01/2022 | 31/01/2023 | SUPRITI ENTERPRISE | 106.12 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 5552/AD | 29/09/2022 | 29/09/2022 | Resource Division | 4.08 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/05/2024 to 30/06/2024. |  | Junior Engineer1, Raidghi Sub Division | ORD/000498/2024-2025 | 559A/RSD | 28/04/2024 | 28/06/2024 | HEMANTA MISTRY | 0.8 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/09/2024 to 31/10/2024. |  | Junior Engineer1, Raidghi Sub Division | ORD/000525/2024-2025 | 685/RSD | 29/08/2024 | 29/10/2024 | HEMANTA MISTRY | 0.8 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/07/2024 to 31/08/2024. |  | Junior Engineer1, Raidghi Sub Division | ORD/000524/2024-2025 | 612/RSD | 28/06/2024 | 28/08/2024 | HEMANTA MISTRY | 0.8 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Laying distribution system of piped water supply at Zone- X of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000658/2024-2025 | 4204/AD | 23/10/2024 | 22/12/2024 | R.S.CONSTRUCTION CO. | 38.62 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01.03.2023 to 30.04.2023 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002426/2022-2023 | 901/RSD | 28/02/2023 | 30/04/2023 | SANKAR HALDER | 0.8 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/11/2023 to 31/12/2023 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/003174/2023-2024 | 335A/RSD | 30/10/2023 | 30/12/2023 | SANKAR HALDER | 0.8 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/01/2024 to 29/02/2024 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/003175/2023-2024 | 419/RSD | 22/12/2023 | 22/02/2024 | SANKAR HALDER | 0.8 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/03/2024 to 30/04/2024 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/003176/2023-2024 | 495A/RSD | 28/02/2024 | 28/04/2024 | SANKAR HALDER | 0.8 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/05/2023 to 30/06/2023 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/003171/2023-2024 | 48/RSD | 28/04/2023 | 28/06/2023 | SANKAR HALDER | 0.8 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/07/2023 to 31/08/2023 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/003172/2023-2024 | 117/RSD | 28/06/2023 | 28/08/2023 | SANKAR HALDER | 0.8 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/09/2023 to 31/10/2023 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/003173/2023-2024 | 255/RSD | 29/08/2023 | 29/10/2023 | SANKAR HALDER | 0.8 | 0 | 0 | 0
Total | [13 empty] | 164.88 | 0 | 0