## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XVI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09556 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-I, Zone-XVI (Payla Bhagabanpur PWSS) including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division |  | ORD/001147/2021-2022 | 5535/AD | 20/01/2022 | 20/01/2023 | FORTUNE ENGINEERING | 18.27 | 13.36 | 73.1 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XVI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09556 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000020/2021-2022 | 5626/AD | 25/01/2022 | 25/01/2022 | Resource Division | 1.39 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XVI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09556 | Retrofitting | Remodeling of laying distribution system of piped water supply at Zone- XVI of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002229/2023-2024 | 921/AD | 08/02/2024 | 09/03/2024 | KARMAKAR CONSTRUCTION | 17.1 | 1.78 | 10.42 | 90
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XVI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09556 | Retrofitting | HIRE CHARGES BILL FOR VEHICLE NO. WB-19J-6364 |  |  | BILL/02359/2023-2024 | BP-2023-24-867 | 29/12/2023 | 29/12/2023 | PINTU MONDAL | 1.08 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XVI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09556 | Retrofitting | HIRE CHARGES BILL OF VEHICLE NO WB-19G-0520 FOR THE MONTH FROM MAY'23 TO AUG'23 |  |  | BILL/02579/2023-2024 | BP-2023-24-698 | 18/11/2023 | 18/11/2023 | AVIK HALDER | 1.54 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XVI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09556 | Retrofitting | Hiring Charges of 1No Motor Cab (Diesel) for the Office fo Assistant Engineer. RWS, Alipore Sub-Division. P.H.E. Dte w.e.f. 01/03/2023 to 31/08/2023) | Assistant Engineer, RWS |  | ORD/001717/2022-2023 | 757/RWS | 21/02/2023 | 21/08/2023 | AVIK HALDER | 0.86 | 0.62 | 72.48 | 20
Total | [13 empty] | 40.25 | 15.76 | 39.16