## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09557 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 3584/AD | 29/07/2022 | 29/07/2022 | Resource Division | 37.95 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XII, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09557 | Retrofitting | Remodeling of distribution system for providing Functional Household Tap Connection (FHTC) to all the households in Zone-XII of Mathurapur-I Block including Operation & Maintenance of scheme for 1 (one) year under "Mega Surface Water based water supply scheme for Falta-Mathurapur, District-South 24-Parganas" under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000115/2022-2023 | 1660/AD | 10/06/2022 | 08/10/2022 | M/S. SUMAN ENTERPRISE | 236.89 | 86.03 | 36.32 | 95
Total | [13 empty] | 274.84 | 86.03 | 31.3