## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Sinking of 29 (Twenty Nine) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P. areas under Canning-I Block-04 nos, Canning-II Block-25 nos due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(As proposed by Smt. Pratima Mondal, Hon'ble M.P (Lok Sabha), Saokat Molla, Hon'ble Member, WBLA) | Assistant Engineer,HQ-I |  | ORD/001560/2021-2022 | 6278/AD | 24/02/2022 | 25/04/2022 | MUNIA ENTERPRISE | 80.53 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Sinking of 21 (Twenty One) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 400 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P. areas under Joynagar-II Block due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (As proposed by Smt. Pratima Mondal, Hon'ble M.P (Lok Sabha), Sri Biswanath Das, Hon'ble Member, WBLA) | Assistant Engineer,HQ-I |  | ORD/001532/2021-2022 | 6307/AD | 25/02/2022 | 26/04/2022 | M/S. S.D. CONSTRUCTION | 77.49 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Temporary water supply at Laxmijanardanpur, Mayrarchak, Paschim Surendranagar, Meherpur and Indranarayanpur MPCS at Patharpratima Block for preventive measurement of SEVERE CYCLONE YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 11.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000170/2021-2022 | 103/KSD | 22/05/2021 | 24/05/2021 | M/S B. ENTERPRISE | 4.76 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Temporary water supply arrangement through Submersible Pump at near Dindapara FP School & Ranjit Giri house (2 nos.) at Sridharnagar GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 27.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000171/2021-2022 | 104/KSD | 22/05/2021 | 24/05/2021 | M/S B. ENTERPRISE | 4.21 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Temporary water supply at various MPCS & Schools (rescue centers) :- Freserganj KPA High School, Debnibas Flood Centre, Bijaybati Flood Centre and Dhaneswar Shiksha Sadan at Namkhana Block for preventive measurement of severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 18.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000178/2021-2022 | 111/KSD | 22/05/2021 | 24/05/2021 | GROWING CONCERN | 4.04 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Temporary water supply arrangement through Submersible Pump at Mahendranagar Khalpar & Mahendranagar Daspara (2 nos.) at Gopalnagar GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000225/2021-2022 | 148/KSD | 25/05/2021 | 27/05/2021 | M/S B. ENTERPRISE | 4.11 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Temporary water supply arrangement through Submersible Pump at Dk. Gopalnagar Gholapara & Daspara near Amullya Das house (2 nos.) at Gopalnagar GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000226/2021-2022 | 149/KSD | 25/05/2021 | 27/05/2021 | M/S B. ENTERPRISE | 4.11 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Temporary water supply arrangement through Submersible Pump at Durga gobinda pur FP School & Rasmoni more (2 nos.) at Gopalnagar GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000229/2021-2022 | 152/KSD | 25/05/2021 | 27/05/2021 | M/S B. ENTERPRISE | 4.11 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Temporary water supply arrangement through Submersible Pump at Nabarun Sangha club & Dulipara more (2 nos.) at Durbachati GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000232/2021-2022 | 155/KSD | 25/05/2021 | 27/05/2021 | M/S B. ENTERPRISE | 4.12 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Temporary water supply arrangement through Submersible Pump at Bhagabatpur Susmita Bera house & Mdhabnagar Sukanta SSK (2 nos.) at Patharpratima GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000234/2021-2022 | 157/KSD | 25/05/2021 | 27/05/2021 | M/S B. ENTERPRISE | 4.11 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Temporary water supply at Banashyamnagar, Gangapur, Purba Sripatinagar and Choto Rakshaskhali MPCS at Patharpratima Block for preventive measurement of SEVERE CYCLONE YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 11.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000169/2021-2022 | 102/KSD | 22/05/2021 | 24/05/2021 | M/S B. ENTERPRISE | 3.99 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Temporary water supply arrangement through Submersible Pump at near Bhunia more Sarat Khara house & Ram Bhunia house (2 nos.) at Ramganga GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000239/2021-2022 | 162/KSD | 25/05/2021 | 27/05/2021 | M/S B. ENTERPRISE | 4.12 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Temporary water supply arrangement through Submersible Pump at Kayamuri Social Keder FP School & Flood centre (2 nos.) at Herambagopalpur GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000241/2021-2022 | 164/KSD | 25/05/2021 | 27/05/2021 | M/S B. ENTERPRISE | 4.11 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Temporary water supply arrangement through Submersible Pump at near Dakshin Durgapur Ayauddin Sk & Karmatirtha (2 nos.) at Digambarpur GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000243/2021-2022 | 166/KSD | 25/05/2021 | 27/05/2021 | M/S B. ENTERPRISE | 4.11 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Temporary water supply arrangement through Submersible Pump at near Mohan Naskar house & Abdul Rozzak house (2 nos.) at Digambarpur GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000245/2021-2022 | 167/KSD | 25/05/2021 | 27/05/2021 | M/S B. ENTERPRISE | 4.11 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Surging of existing tube well with chemical treatment and bucket washing at different location (5 nos) of Patharpratima Block affected by SEVERE CYCLONE YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000284/2021-2022 | 330/KSD | 03/06/2021 | 18/06/2021 | M/S B. ENTERPRISE | 1.05 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Surging of 12 nos. existing tube well with chemical treatment and bucket washing at different location of G.P. - Mousuni, Blcok - Namkhana due to affected by severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000286/2021-2022 | 332/KSD | 03/06/2021 | 18/06/2021 | KRISHNA CONSTRUCTION | 2.89 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Temporary water supply arrangement through Submersible Pump at near Dindapara Rabin Das house & Jagannath Manna house (2 nos.) at Sridharnagar GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000263/2021-2022 | 169/KSD | 25/05/2021 | 27/05/2021 | M/S B. ENTERPRISE | 4.11 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Temporary water supply arrangement through Submersible Pump at near Gobindapur Indra more Lalu Barui house & Indrapur bazar (2 nos.) at G plot GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000265/2021-2022 | 171/KSD | 25/05/2021 | 27/05/2021 | M/S B. ENTERPRISE | 4.11 | 0 | 0 | 0
20 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Sinking of 15(Fifteen) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Patharpratima Block (Herambagopalpur G.P.-03 no,S/Purnachandrapur G.P.- 02 no,Achintyanagar-02 no, Digambarpur G.P.- 02 no,Dk.Raypur G.P.- 02, Ramganga G.P.- 04 no) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) | Assistant Engineer,HQ-I |  | ORD/001393/2021-2022 | 6145/AD | 21/02/2022 | 07/04/2022 | ARSHAD ALI MOLLA | 44.68 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Sinking of 11(Eleven) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Gosaba Block (Kumirmari G.P.-07 no, Radhanagar Taranagar G.P-04 no) due to affected by super Cyclon-"YAASH" in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-A) | Assistant Engineer,HQ-I |  | ORD/001412/2021-2022 | 6155/AD | 21/02/2022 | 07/04/2022 | MD. NAZRUL ISLAM GAZI | 37.2 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Sinking of 02 (Two) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P. areas under Canning-I Block (Hatpukuria G.P.-02 no) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A-I) | Assistant Engineer,HQ-I |  | ORD/001386/2021-2022 | 6138/AD | 21/02/2022 | 08/03/2022 | S.B. CONSTRUCTION | 5.55 | 0 | 0 | 0
23 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Sinking of 06(Six) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 330 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Namkhana Block (Budhakhali G.P.-06 no) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-B) | Assistant Engineer,HQ-I |  | ORD/001403/2021-2022 | 6150/AD | 21/02/2022 | 23/03/2022 | SONIA ENTERPRISE | 19.12 | 0 | 0 | 0
24 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Development of 02 (two) nos. TW due to inundation of river saline water of Cyclone ' YAAS' 2021 at Kanthalberia W/S Scheme (TW-1) of Basanti Block & Dharmatala W/S Scheme (TW-4) of Canning-I Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001118/2021-2022 | 255/CSD | 07/06/2021 | 07/07/2021 | SURYA ENTERPRISE | 0.98 | 0 | 0 | 0
25 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Sinking of 05(Five) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 350 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Joynagar-I Block (Chaltaberia G.P.- 02 no, Dosha Chandenesar G.P.- 03 no ) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. [ PART-D ] | Assistant Engineer,HQ-I |  | ORD/001533/2021-2022 | 6275/AD | 24/02/2022 | 26/03/2022 | PAL AGENCY | 15.43 | 0 | 0 | 0
26 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Sinking of 06(Six) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Sagar Block (Rudranagar G.P.- 02 no, , Ganga Sagar G.P.- 04 no) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-E) | Assistant Engineer,HQ-I |  | ORD/001508/2021-2022 | 6265/AD | 24/02/2022 | 26/03/2022 | HARIDAS DUTTA | 21.09 | 0 | 0 | 0
27 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Sinking of 03(Three) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 350 mtr (Average) depth fitted with India Mark-II \DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Joynagar-I Block ( Narayanitala G.P.- 03 no ) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. [ PART-F ] | Assistant Engineer,HQ-I |  | ORD/001534/2021-2022 | 6277/AD | 24/02/2022 | 11/03/2022 | PAL AGENCY | 9.18 | 0 | 0 | 0
28 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 5106/AD | 23/12/2021 | 23/12/2021 | Resource Division | 20.08 | 0 | 0 | 0
29 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 3691/AD | 02/08/2022 | 02/08/2022 | Resource Division | 20.08 | 0 | 0 | 0
30 | SOUTH 24 PARGANAS |  | Alipore Division | Sinking of 125 (One Hundred Twenty Five) nos. Mark - II hand pump tubewells to mitigate immediate crisis of drinking water due to super Cyclone YAASH affected blocks in the District of South 24 Parganas. | SM/09727 | Disaster | Material Requisition To Resource Division |  |  | RTOR000026/2022-2023 | 2534/AD | 28/06/2022 | 28/06/2022 | Resource Division | 5.62 | 0 | 0 | 0
Total | [13 empty] | 423.2 | 0 | 0