## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IX, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09769 | Retrofitting | Laying distribution system of piped water supply at Zone-IX of Mathurapur - II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001482/2021-2022 | 6260/AD | 24/02/2022 | 10/02/2025 | JAL PRAVAHIKA PVT. LTD. | 409.34 | 0 | 0 | 90
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IX, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09769 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to the households under Purba Sridharpur mouza (JL No. 131) and Nagendrapur Mouza (JL No. 132)in Mathurapur-II, Zone-IX under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000348/2022-2023 | 4075/AD | 18/08/2022 | 01/05/2024 | JAL PRAVAHIKA PVT. LTD. | 84.29 | 0 | 0 | 99
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IX, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09769 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to the households under Damkal mouza (JL No. 133) in Mathurapur-II, Zone-IX under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000347/2022-2023 | 4074/AD | 18/08/2022 | 17/10/2022 | M/S B.M. CONSTRUCTION | 62.36 | 40.14 | 64.38 | 90
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IX, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09769 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 3583/AD | 29/07/2022 | 29/07/2022 | Resource Division | 73 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IX, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09769 | Retrofitting | Land development of OHR site at Zone - IX, Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001802/2022-2023 | 932/RSD | 10/03/2023 | 09/04/2023 | G.B. CONSTRUCTION & CO. | 2.27 | 2.26 | 99.64 | 10
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-IX, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme | SM/09769 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000647/2023-2024 | 250/AD | 15/01/2024 | 15/01/2024 | Resource Division | 21.81 | 0 | 0 | 0
Total | [13 empty] | 653.08 | 42.41 | 6.49