## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Ganeshpur (Left Out) W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001043/2021-2022 | 2274/AD | 06/09/2021 | 13/09/2021 | ROY CHOWDHURY ASSOCIATES | 3.25 | 3.25 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Route Survey for Providing FHTC at Ganeshpur Left Out W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001024/2021-2022 | 538/KSD | 01/09/2021 | 21/09/2021 | M/S R.DUTTA & CO. | 4.59 | 4.58 | 99.85 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Route Survey for Providing FHTC at Ganeshpur Left Out W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001612/2021-2022 | 611/KSD | 27/09/2021 | 04/10/2021 | M/S R.DUTTA & CO. | 1.55 | 0.88 | 56.82 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-V) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001895/2020-2021 | 1317/KSD | 23/02/2021 | 05/03/2021 | M/S. SUNITY ENTERPRISE | 4.74 | 4.36 | 92.01 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Krishnanagar (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001811/2020-2021 | 1250/KSD | 23/02/2021 | 05/03/2021 | M/S. SUNITY ENTERPRISE | 4.79 | 4.73 | 98.6 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia Uttar Dakshin (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001841/2020-2021 | 1272/KSD | 23/02/2021 | 05/03/2021 | M/S. SUNITY ENTERPRISE | 4.74 | 4.68 | 98.86 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gheri Uttar, Dakshin and others (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000133/2021-2022 | 388/KSD | 07/07/2021 | 22/07/2021 | UNIQUE CONSTRUCTION (II) | 4.39 | 4.13 | 94.19 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia Uttar Dakshin (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001807/2020-2021 | 1245/KSD | 23/02/2021 | 05/03/2021 | M/S. SUNITY ENTERPRISE | 4.79 | 4.75 | 99.07 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gheri Uttar (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001844/2020-2021 | 1275/KSD | 23/02/2021 | 05/03/2021 | UNIQUE CONSTRUCTION (II) | 4.38 | 3.55 | 81.05 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gheri Uttar (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001798/2020-2021 | 1240/KSD | 23/02/2021 | 05/03/2021 | UNIQUE CONSTRUCTION (II) | 4.7 | 4.55 | 96.81 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001858/2020-2021 | 1248/KSD | 23/02/2021 | 05/03/2021 | FIDERE MARINE SERVICES PVT. LTD. | 4.7 | 3.76 | 79.98 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001851/2020-2021 | 1282/KSD | 23/02/2021 | 05/03/2021 | FIDERE MARINE SERVICES PVT. LTD. | 4.6 | 3.92 | 85.19 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gheri Uttar, Dakshin and others (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000130/2021-2022 | 385/KSD | 07/07/2021 | 22/07/2021 | UNIQUE CONSTRUCTION (II) | 4.39 | 4.18 | 95.34 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Krishnanagar (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001838/2020-2021 | 1269/KSD | 23/02/2021 | 05/03/2021 | M/S. SUNITY ENTERPRISE | 4.78 | 4 | 83.76 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( Ganeshpur (Left out Areas) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000489/2022-2023 | 302/AD | 12/04/2022 | 27/05/2022 | LEMNISCATE | 8.66 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction of 01 no. Pump House for Ganeshpur Left Out Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1000] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000856/2022-2023 | 6939/AD | 18/11/2022 | 04/06/2025 | M/S PRADIP KUMAR PAL | 104.35 | 66.43 | 63.66 | 100
17 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2022-2023 | 3904/AD | 12/08/2022 | 12/08/2022 | Resource Division | 348.05 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000092/2022-2023 | 5589/AD | 29/09/2022 | 29/09/2022 | Resource Division | 14.31 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Construction of 1 no. 550 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Ganeshpur Left Out Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 1500] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000301/2023-2024 | 1493/AD | 14/07/2023 | 09/05/2024 | SPA ENTERPRISE | 592.38 | 37.81 | 6.38 | 20
20 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Making and fixing of permanent display board at headwork site of Ramratanpur, Suryanagar Zone - I & II, Ganeshpur Left Out area PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002147/2023-2024 | 946/KSD | 19/12/2023 | 24/12/2023 | ANANTA KUMAR GIRI | 0.63 | 0.16 | 24.99 | 100
21 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000258/2023-2024 | 3063/AD | 28/09/2023 | 28/09/2023 | Resource Division | 1.2 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 5th Tubewell Site for Augmentation of Ganeshpur Left Out W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/09922) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000204/2024-2025 | 2587/AD | 19/06/2024 | 03/08/2024 | R. UNIQUE CONSTRUCTION | 9.7 | 0 | 0 | 0
23 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 5th tubewell Site for Augmentation of Ganeshpur Left Out Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09922) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000205/2024-2025 | 2588/AD | 19/06/2024 | 03/08/2024 | R. UNIQUE CONSTRUCTION | 5.6 | 0 | 0 | 0
24 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Ganeshpur Left Out W/S Scheme, Block - Kakdwip under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09922) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division | ORD/000163/2024-2025 | 2514/AD | 15/06/2024 | 15/07/2024 | SHREE J M CONSTRUCTION | 20.39 | 4.94 | 24.23 | 100
25 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000674/2023-2024 | 440/AD | 24/01/2024 | 24/01/2024 | Resource Division | 4.29 | 0 | 0 | 0
26 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Ganeshpur (Left out Areas) PWSS for Providing Functional Household Tap Connection (FHTC) | SM/09922 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000804/2023-2024 | 649/AD | 30/01/2024 | 30/01/2024 | Resource Division | 10.22 | 0 | 0 | 0
Total | [13 empty] | 1180.17 | 164.66 | 13.95